## Summary
SEO Audit: salesroads.com
Audit date | 2026-10-01
Site | https://salesroads.com/
Overall health | Needs Work
Method | Live crawl of all 390 sitemap URLs (raw HTML: titles, metas, headings, canonicals, robots, JSON-LD, links), robots.txt, 5 sub-sitemaps, cached vs uncached TTFB, plus SERP checks for core keywords, plus client-provided Semrush exports (Domain Overview, Organic Pages, Position Changes; Oct 1, 2026). Stack: WordPress + Elementor Pro + Rank Math on WP Engine / Cloudflare.
Findings by priority
Priority | Total | Done | Open | % Done
Critical | 10 | 0 | 10 | 0%
Important | 16 | 0 | 16 | 0%
Nice-to-have | 6 | 0 | 6 | 0%
Total | 32 | 0 | 32 | 0%
Top critical issues
C-01 | 74-char site name appended to 153 page titles
C-02 | Junk WP username 'jjUplds9j0das0' published as Article author; users REST API open
C-03 | Thank-you, opt-in, PPC and duplicate pages are indexable and in the sitemap
C-04 | Blog posts cannibalize service pages for money keywords
C-05 | Slow uncached server response (TTFB)
C-06 | Generic or internal titles on key pages
C-07 | 43 pages have no meta description
C-08 | Missing H1 on key pages
C-09 | www.salesroads.com ranks as a separate homepage (Semrush)
C-10 | Temporary 307 redirect chains into top service pages
What's working
Public pricing on /pricing/ (rare among competitors) – a real asset for 'cost' queries.
33 case studies with named clients (Shell, Paylocity, Parker Hannifin, Clutch, Crewhu) and Challenge > Solution > Results structure.
Original formats: Sell Like a Leader podcast (42 episodes), Sales Feud, SDR hiring white paper, monthly newsletter.
Homepage ranks on page 1 for 'sales outsourcing company' (point-in-time sample).
/lead-generation-services/ is a strong commercial page: 21% of organic traffic, ranks for 'lead generation services' (6.6K/mo) and 'lead generation companies' (4.4K/mo) (Semrush).
HTTPS, self-referencing canonicals on all 390 URLs, correct 404s, OG/Twitter cards, Rank Math sitemaps incl. video sitemap.
Tabs
Action Tracker | All findings with priority, recommendation, owner and status
Quick Wins | Top 10 actions to do first
Title & Meta Rewrites | Copy-paste titles/metas with length checks
Content Plan | New and rebuilt pages, with target queries and briefs
Blog Cleanup | Merge / refresh / prune decisions for existing posts
Keyword Clusters | Target clusters; fill in volumes from your SEO tool
Semrush Data | Traffic snapshot, top pages and new rankings from the Semrush exports
External Checks | Items to verify with GSC, PSI, Ahrefs, Screaming Frog
Sources | Evidence URLs

## Action Tracker
SalesRoads.com SEO Audit – Action Tracker
Yellow columns (Owner, Due Date, Status, Notes) are for your team to fill in. Status 'Done' greys out the row and updates the Summary tab. Row 5 shows an example owner.
ID | Category | Priority | Finding | Affected URLs / Evidence | Why it matters | Recommendation | Effort | Impact | Owner | Due Date | Status | Notes
C-01 | On-Page | Critical | 74-char site name appended to 153 page titles | '- Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads' on /inbound-appointment-setting/ (101 chars), /logistics-supply-chain-industry/ (107), /manufacturing-industry-landing-page/ (109), /outbound-email-services/ (97)… | Titles truncate at ~60 chars; keyword stuffed into 150+ titles dilutes relevance and competes with the homepage; leaks 'Industry Page' / 'Landing Page' names. | Settings > General > Site Title (or Rank Math > Global Meta > Website Name) = 'SalesRoads'. Keep format %title% %sep% %sitename% with '¦'. Then apply the 'Title & Meta Rewrites' tab. | Low | High | SEO lead |  | Not started | Example row - replace with your owner
C-02 | Technical | Critical | Junk WP username 'jjUplds9j0das0' published as Article author; users REST API open | Article + Person schema on homepage and 15 other pages; /wp-json/wp/v2/users returns 200 | Negative E-E-A-T signal (homepage is not an Article) and exposes half of an admin login; user enumeration is trivial. | Rank Math > Titles & Meta > Pages > Schema Type = None/WebPage. Set the user's public display name. Block /wp-json/wp/v2/users for anonymous requests; consider renaming the account. | Low | High |  |  | Not started
C-03 | Technical | Critical | Thank-you, opt-in, PPC and duplicate pages are indexable and in the sitemap | /request-received/, /meet-the-team/, /communication-opt-in-settings/, /vsa/ (16 of 20 headings = homepage), /appointment-setting-landing-page/, /lead-generation-landing-page/, /sales-outsourcing-landing-page/, /manufacturing-industry-landing-page/, /healthcare-industry-landing-page/ | PPC duplicates compete with the real service pages; thank-you pages in search pollute conversion tracking. | Add noindex and remove from the sitemap (Rank Math > Advanced on each page). Optionally 301 /vsa/ to / with a banner. | Low | High |  |  | Not started
C-04 | Content | Critical | Blog posts cannibalize service pages for money keywords | 40 URLs target 'appointment setting', 55 'lead generation', 43 'outsourcing'. /outsourcing/lead-generation-services/ shares the slug of /lead-generation-services/. Semrush: 'top outsourced sdr providers' ranks with / (#23) AND /outsourced-sdr-services/ (#61); 'appointment setting solutions' ranks with a blog post. See 'Blog Cleanup'. | Google alternates between URLs; service pages absent from top 9 for 'B2B appointment setting services', 'outsourced SDR services', 'B2B cold calling services'. | Confirm in GSC (query > Pages). Merge + 301 duplicates; re-angle remaining posts to informational intent; link to service page with exact-match anchors. | Medium | High |  |  | Not started
C-05 | Technical | Critical | Slow uncached server response (TTFB) | Cache MISS TTFB 1.9-3.2s on every page tested; 6-9s observed during crawl (/compliance-services-industry-page/ 9.7s). HTML cache max-age=600. | Googlebot mostly hits cold cache on 348 posts; slow TTFB lowers crawl rate and LCP. | Enable Cloudflare APO / edge HTML caching with purge-on-publish; profile origin (Query Monitor / New Relic); remove 'Crawl-delay: 10' from robots.txt. | Medium | High |  |  | Not started
C-06 | On-Page | Critical | Generic or internal titles on key pages | Blog, About Us, Careers, Why Choose Us, Methodology, Client Success, Sales Executives, Request a Quote, 'Insurtech Industry Page' | Highest-intent pages give Google little to rank and earn low CTR. | Apply the 'Title & Meta Rewrites' tab. | Low | High |  |  | Not started
C-07 | On-Page | Critical | 43 pages have no meta description | 25 podcast episodes, 5 outsourcing, 5 leadership posts, 4 case studies (Clutch, Bold Penguin, Rudholm, ZoomIn), VSA announcement | Google auto-generates snippets, often from boilerplate. | Write 140-155 char descriptions; lead case studies with the result metric. | Medium | Medium |  |  | Not started
C-08 | On-Page | Critical | Missing H1 on key pages | /blog/, /request-a-quote/, /all-industry-pages/, /communication-opt-in-settings/ | Weak topical signal on hub and conversion pages. | Add one descriptive H1 to each (e.g. 'B2B Sales & Outbound Prospecting Blog'). | Low | Medium |  |  | Not started
C-09 | Technical | Critical | www.salesroads.com ranks as a separate homepage (Semrush) | Semrush: https://www.salesroads.com/ = 12.0% of organic traffic, 34 keywords, 59 referring domains / 125 backlinks. Audit proxy blocked www so redirect unverified. | Homepage signals may be split across two hosts. | curl -sI https://www.salesroads.com/ and http://www… must return ONE 301 to https://salesroads.com/ (path preserved). Set in WP Engine Domains or Cloudflare redirect rule; check Google-selected canonical in GSC URL Inspection. | Low | High |  |  | Not started
C-10 | Technical | Critical | Temporary 307 redirect chains into top service pages | /leadgeneration 301>307>301; /lead-generation 307>301; /appointment-setting 307>301; /contact 301>301; /about and /case-studies 404 | /lead-generation-services/ earns 21% of organic traffic; 307s don't reliably pass equity/canonical signals. | Replace with single 301s to final trailing-slash URLs (WP Engine redirect rules or Rank Math Redirections); add 301 /about > /about-us/, /case-studies > /client-success/. | Low | High |  |  | Not started
I-01 | Technical | Important | Self-serving / invalid review markup | /reviews/ Product + AggregateRating (image is a .webm); /appointment-setting-services/ uses lowercase 'product' / 'aggregateRating' (invalid) | Google does not show stars for self-reviews; marking a service as Product for stars risks a structured-data manual action. | Remove Product/AggregateRating wrappers; keep attributed Review items only; fix or delete the lowercase block. | Low | Medium |  |  | Not started
I-02 | Technical | Important | 340 of 347 BlogPostings lack datePublished/dateModified; no date shown on posts | Rank Math BlogPosting schema; Elementor single-post template | Freshness signal missing for 'how-to' and 'cost' queries and AI Overviews. | Enable dates in Rank Math post schema; show 'Updated {date}' in the single-post template. | Low | Medium |  |  | Not started
I-03 | Technical | Important | Organization schema is weak | name = 'SalesRoads ¦ America's Most-Trusted…', description 'All Things Sales Outsourcing', logo 'Untitled-Project-38.png', no sameAs | Muddies the brand entity / Knowledge Panel. | name 'SalesRoads', legalName 'Homebase-USA', foundingDate, sameAs (LinkedIn, Clutch, G2, YouTube, podcast); rename logo file. | Low | Medium |  |  | Not started
I-04 | Technical | Important | Unidentified third-party script on all pages | consortiumventure24.com/js/812387.js (synchronous) + noscript pixel; pattern matches B2B visitor-ID trackers | Render-blocking and an unknown script is a security risk. | Confirm with marketing it is intentional and contracted; if yes load async via GTM; if not remove now. | Low | Medium |  |  | Not started
I-05 | On-Page | Important | Multiple H1s on 15 pages; headings used for styling | /outbound-email-services/ and /sales-feud/ repeat H1; phone number = H3 twice per page; 'Request a Quote' = H5; team names H2/H4/H6 | Messy outline across all 390 pages. | One H1 per page; change header/footer/CTA headings to <p> in Elementor templates. | Low | Medium |  |  | Not started
I-06 | On-Page | Important | Homepage H1 is lowercase eyebrow 'sales outsourcing agency' | Real headline 'We'll build your dream pipeline.' is H2 | Main page H1 wastes its keyword signal. | H1: 'B2B Sales Outsourcing & Appointment Setting That Builds Your Pipeline'; eyebrow becomes <p>. | Low | Medium |  |  | Not started
I-07 | On-Page | Important | Meta descriptions too long or junk | 130 over 160 chars; /about-us/ 'SALESROADS', /request-a-quote/ 'BOOK A CALL', /pricing/ 'SalesRoads Pricing', /fed-sled-industry/ 'FED&SLED INDUSTRY'; templated '+19 years' on industry pages | Truncated or unpersuasive snippets. | Rewrite to 140-155 chars: keyword + proof + CTA. | Medium | Medium |  |  | Not started
I-08 | Performance | Important | Heavy front-end | 260-400 KB HTML; 19 stylesheets; 18 render-blocking scripts; 54 KB inline CSS; all 43 homepage images PNG/JPG; fonts from Google + fonts.bunny.net | Hurts LCP/INP on mobile. | Elementor optimized DOM/asset loading; defer jQuery-dependent scripts; delay chat widget; self-host one font; WebP/AVIF. Verify in PageSpeed Insights. | Medium | Medium |  |  | Not started
I-09 | Content | Important | No page answers 'SalesRoads reviews / alternatives' | G2, Cleverly, SalesBread, Salesforge, OutboundSalesPro, Alleyoop, RemoteAides own the SERP; some quote outdated pricing | Bottom-of-funnel buyers see competitor framing. | Build the reviews & alternatives page plus comparison pages (see 'Content Plan'). | Medium | High |  |  | Not started
I-10 | Content | Important | Stale years in 17 titles | '2024: 9 Best B2B Lead Generation Courses', 'Is Cold Calling Still Effective in 2024?', '…in 2023', 'Strategies for 2025' (URL says 2024) | Looks outdated; lowers CTR. | Refresh content and update or drop the year. | Medium | Medium |  |  | Not started
I-11 | Content | Important | Contradictory track-record claims | '+19 years' (37), '19+' (16), '17+' (8), '15+' (10), '18+' (6), 'since 2007'; third parties say founded 2006 | Inconsistent facts undermine trust (E-E-A-T). | Pick one fact (e.g. 'Since 2007') and replace everywhere incl. metas and schema. | Low | Medium |  |  | Not started
I-12 | Technical | Important | Blog pagination canonicalises to /blog/; category hubs not in sitemap | /blog/?e-page-fdfa077=2 canonical = /blog/; /category/tactics/ etc. indexable with slug titles | Older posts reachable only via sitemap/related widgets. | Real paginated URLs (/blog/page/2/); add categories to sitemap with intro copy and proper titles. | Medium | Medium |  |  | Not started
I-13 | Content | Important | Thin case studies; no case-study hub | Copperweld, Factor, Agility, Safecor, Shell ~550-620 words incl. boilerplate; /client-success/ is a logo wall | Best proof content is underused. | Build /case-studies/ hub filterable by industry/service; expand thin studies with metrics. | Medium | Medium |  |  | Not started
I-14 | Content | Important | High-traffic informational and job-description pages have no path to a service | /tactics/qualifying-leads-definition/ (6.0% of traffic), /leadership/sales-executive-meaning/ (3.6%), /leadership/appointment-setting-job-description/ (1.7%), /leadership/lead-generation-job-description/ (1.2%), /leadership/business-development-and-sales-manager-job-description/ (0.7%; new #13 for 'manager in business development', 3.6K/mo) | Job-description searchers are often hiring managers, i.e. buyers. Traffic currently doesn't convert. | Add in-content CTA: 'Hiring an appointment setter? Compare the cost of an outsourced SDR' > /pricing/ and /outsourcing/in-house-sdr-costs/. Keep these posts (do not prune). | Low | Medium |  |  | Not started
I-15 | Content | Important | Link equity sits on the homepage and two blog posts, not on service pages | Semrush: home 668 referring domains; /leadership/ai-in-sales/ 146; /leadership/sales-and-business-development-courses/ 110; /lead-generation-services/ 60. Top referrers are directories (alivelink.org 1,703 links, neudesk.com 615, gitnux.org 323). | Weak service pages (SDR, cold calling) lack authority; directory links won't move rankings. | Refresh link-magnet posts in place (keep URLs); add contextual links from them to /outsourced-sdr-services/, /appointment-setting-services/, /outbound-calling-services/. Pursue digital PR with data assets (pricing benchmarks, SDR hiring report). Don't disavow unless a manual action. | Medium | Medium |  |  | Not started
I-16 | Content | Important | Organic traffic down ~40% from 2025 peak; only 85 top-3 keywords | Semrush: 3.1K/mo vs ~5.5K peak; positions 1-3: 85, 4-10: 285, 11-20: 453; 72.7% informational keywords | Visibility is eroding; 453 keywords are one push from page 1. | Execute critical fixes first, then refresh the 11-20 'striking distance' pages (Semrush filter: positions 11-20, sort by volume). | High | High |  |  | Not started
N-01 | On-Page | Nice-to-have | 14 template images lack alt text | Menu icons (appointment-setting.png, lead-gen.png, case-studies.png…) on every page | Accessibility + image search. | Add alt in Media Library or alt="" if decorative. | Low | Low |  |  | Not started
N-02 | On-Page | Nice-to-have | UTM parameters on internal links | /pricing/?utm_source=pricing… (14), /request-a-quote/?utm_…, /careers/?utm_… | Resets GA4 session source. | Track CTA clicks with GA4 events instead. | Low | Low |  |  | Not started
N-03 | On-Page | Nice-to-have | Internal links to redirects / noindex pages | 6 links via 301 (e.g. /tactics/cold-call-structure/); 1 link to noindexed /leadership/the-3-ai-lessons-…/; 5 date archives redirect to / | Wasted crawl and link equity. | Point links at final URLs; publish or remove the noindexed post. | Low | Low |  |  | Not started
N-04 | Technical | Nice-to-have | Tag robots inconsistent | 9 tags noindex; /tag/hiring/ index | Thin archive indexed. | Noindex /tag/hiring/. | Low | Low |  |  | Not started
N-05 | Technical | Nice-to-have | Video sitemap quality | 17 of 114 videos use YouTube boilerplate description; 20 titles carry the long suffix | Poor video rich-result eligibility. | Write one-sentence descriptions; C-01 fixes titles. | Low | Low |  |  | Not started
N-06 | Technical | Nice-to-have | No llms.txt | /llms.txt returns 404; site has 'Ask ChatGPT / Claude / Perplexity' buttons | Helps AI assistants find canonical service, pricing and case-study URLs. | Add llms.txt (Rank Math can generate). | Low | Low |  |  | Not started

## Quick Wins
Quick Wins – do these first
# | Action | Tracker ID | Est. effort | Status (from tracker)
1 | Set WordPress Site Title to 'SalesRoads' (removes 74-char suffix from 153 titles) | C-01 | 5 min | Not started
2 | Noindex + remove from sitemap: thank-you, opt-in, /vsa/ and 5 *-landing-page URLs | C-03 | 15 min | Not started
3 | Pages schema Article > WebPage; fix display name for jjUplds9j0das0; block users API | C-02 | 15 min | Not started
4 | Identify or remove the consortiumventure24.com script | I-04 | 15 min | Not started
5 | Paste titles + metas from 'Title & Meta Rewrites' for 25 commercial pages | C-06 | 1-2 hrs | Not started
6 | Fix Elementor heading templates: one H1, phone/CTA headings to <p> | I-05 | 1 hr | Not started
7 | Remove self-serving Product/AggregateRating schema | I-01 | 30 min | Not started
8 | Enable datePublished/dateModified + visible 'Updated' date on posts | I-02 | 30 min | Not started
9 | Rename/merge /outsourcing/lead-generation-services/ | C-04 | 30 min | Not started
10 | Cloudflare APO / edge HTML caching; remove Crawl-delay | C-05 | 1 hr | Not started
11 | Confirm www > apex is a single 301; check Google-selected canonical | C-09 | 15 min | Not started
12 | Replace 307 redirect chains (/leadgeneration, /lead-generation, /appointment-setting, /contact) with single 301s | C-10 | 15 min | Not started
13 | Add 'Hiring an SDR? Compare costs' CTA to job-description posts + service CTA on qualifying-leads-definition | I-14 | 1 hr | Not started

## Title & Meta Rewrites
URL | Current title (live HTML) | Proposed title | Proposed meta description | Title length | Meta length
/ | Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | B2B Sales Outsourcing & Appointment Setting ¦ SalesRoads | US-based SDR teams that book qualified B2B meetings for you. Trusted by Shell, Paylocity & Clutch. Transparent pricing, cancel anytime. Get a quote. | 56 | 148
/appointment-setting-services/ | B2B Appointment Setting Services ¦ SalesRoads | B2B Appointment Setting Services ¦ SalesRoads | Onshore SDRs who book qualified meetings with decision-makers. 937 appointments for AchieveIt. See pricing and case studies, then request a quote. | 45 | 146
/outsourced-sdr-services/ | Outsourced SDR Services ¦ SDR Outsourcing Company - SalesRoads | Outsourced SDR Services: Dedicated US Reps ¦ SalesRoads | Get a fully managed outbound SDR team (reps, coaching, data ops and training) for less than the cost of hiring in-house. See pricing. | 55 | 133
/outbound-calling-services/ | B2B Cold Calling Services ¦ Cold Calling Outsourcing - SalesRoads | B2B Cold Calling Services by US-Based SDRs ¦ SalesRoads | Experienced onshore callers who reach decision-makers, qualify interest and book meetings with B2B decision-makers. Get a quote. | 55 | 128
/lead-generation-services/ | Outsourced Lead Generation Services: B2B Lead Generation Company | B2B Lead Generation Services ¦ SalesRoads | Researched, phone-verified B2B leads and market-research lead generation that fill your pipeline with real buyers. See case studies and pricing. | 41 | 144
/pricing/ | Pricing - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | SalesRoads Pricing: Outsourced SDR & Appointment Setting | See exactly what an outsourced SDR program costs and how it compares with building in-house. Plans, what's included and FAQs. | 56 | 125
/blog/ | Blog | B2B Sales Blog: Cold Calling, SDR & Lead Gen ¦ SalesRoads | Practical guides on cold calling, outbound email, SDR management and lead generation from the team that has booked thousands of B2B meetings. | 57 | 141
/about-us/ | About Us | About SalesRoads: US-Based Sales Development Since 2007 | Meet the onshore sales development team behind 33+ published client wins, 3× Inc. 5000 and a 4.9 Clutch rating. Our story, mission and people. | 55 | 142
/why-us/ | Why Choose Us | Why SalesRoads: Onshore SDRs & Proven Results | Senior US-based reps, transparent reporting, no long-term contracts. See how SalesRoads differs from other appointment setting agencies. | 45 | 136
/reviews/ | Client Reviews | SalesRoads Reviews: 4.9★ Client Ratings & Testimonials | Read verified client reviews of SalesRoads' appointment setting and SDR services from Clutch and G2, plus answers to common questions. | 54 | 134
/inbound-appointment-setting/ | Inbound Appointment Setting - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Inbound Appointment Setting & Lead Response ¦ SalesRoads | Stop letting ready buyers slip through the cracks. Our SDRs follow up on inbound leads and turn them into booked meetings. | 56 | 122
/outbound-email-services/ | Outbound Email Services - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Outbound Email Services: B2B Cold Email ¦ SalesRoads | Personalized B2B cold email campaigns written and run by SDRs, with deliverability managed and replies converted into meetings. | 52 | 127
/account-reactivation/ | Account Reactivation - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Account Reactivation Services: Win Back Clients ¦ SalesRoads | Turn dormant and lapsed accounts back into revenue with a dedicated reactivation team. Typical results and how the program works. | 60 | 129
/saas-industry/ | SaaS Industry - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | SaaS Appointment Setting & Lead Generation ¦ SalesRoads | SDRs who understand SaaS buying committees and book demos with qualified decision-makers. See SaaS case studies and results. | 55 | 124
/healthcare-industry/ | Healthcare Industry - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Healthcare Appointment Setting & B2B Lead Gen ¦ SalesRoads | Reach decision-makers at IDNs, hospitals and private practices with SDRs trained in healthcare buying cycles. See healthcare case studies. | 58 | 138
/manufacturing-industry-page/ | Manufacturing Industry Page - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Manufacturing Lead Generation & Appointment Setting | SDRs who speak the language of manufacturing, from the plant floor to procurement. Book meetings with engineering and ops buyers. | 51 | 129
/fintech-industry/ | Fintech Industry - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Fintech Lead Generation & Appointment Setting ¦ SalesRoads | Book meetings with banks, credit unions and fintech buyers. Compliance-aware SDRs with fintech case studies to prove it. | 58 | 120
/fed-sled-industry/ | FED & SLED Industry - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Government (FED & SLED) Appointment Setting ¦ SalesRoads | Reach federal, state, local and education buyers. SDRs who navigate public-sector procurement and book qualified meetings. | 56 | 122
/insurtech-industry-page/ | Insurtech Industry Page - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Insurtech Lead Generation & Appointment Setting | Book meetings with carriers, MGAs and agencies. SDRs experienced in insurtech sales cycles. See Bold Penguin and InnSure results. | 47 | 129
/logistics-supply-chain-industry/ | Logistics & Supply Chain Industry - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Logistics Lead Generation & Appointment Setting | Reach shippers, 3PLs and supply-chain leaders with SDRs who know the industry. See Unishippers results. | 47 | 103
/compliance-services-industry-page/ | Compliance Services Industry Page - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Compliance Services Lead Generation ¦ SalesRoads | Book meetings with risk, legal and compliance buyers. See how SalesRoads delivered 807 opportunities for Protecht. | 48 | 114
/all-industry-pages/ (> /industries/) | All Industry Pages - Sales Outsourcing Company ¦ Outsourced Sales Team Services - SalesRoads | Industries We Serve: B2B Appointment Setting ¦ SalesRoads | Appointment setting and lead generation tailored to SaaS, healthcare, fintech, manufacturing, government and more. | 57 | 114
/client-success/ | Client Success | Client Success Stories & Case Studies ¦ SalesRoads | How SalesRoads booked 937 appointments for AchieveIt, 807 opportunities for Protecht and more. Browse results by industry. | 50 | 122
/methodology/ | Methodology | Our Outbound Sales Methodology ¦ SalesRoads | How we research, message, call and qualify to book meetings that close: the SalesRoads process, step by step. | 43 | 109
/careers/ | Careers | Sales Development Careers at SalesRoads | Join a sales development team built for growth: training, coaching and a culture that feels like home. See open SDR roles. | 39 | 122
Lengths over 60 (title) / 160 (meta) turn yellow. Check every proof point (client names, numbers, 'cancel anytime', Clutch rating) against current facts before publishing.

## Content Plan
Group | Type | Proposed URL | Target queries | Intent | Priority | Brief / key elements | Owner | Status
A | Reviews | /salesroads-reviews/ (or expand /reviews/) | salesroads reviews; salesroads alternatives; salesroads pricing | Commercial | Critical | Clutch/G2 ratings with links, current pricing, who SalesRoads is NOT a fit for, comparison on onshore reps, terms, reporting. WebPage + FAQPage schema. |  | Not started
A | Comparison | /compare/salesroads-vs-superhuman-prospecting | superhuman prospecting alternative; vs salesroads | Transactional | Important | Semrush #2 organic competitor (20% overlap). Feature/pricing/contract table, onshore vs offshore, minimum term, best-for. |  | Not started
A | Comparison | /compare/salesroads-vs-sales-focus | sales focus inc alternative; vs salesroads | Transactional | Important | Semrush #3 organic competitor (19%). Same template. |  | Not started
A | Comparison | /compare/salesroads-vs-salesbread | salesbread alternative; vs salesroads | Transactional | Important | Semrush #5 (15%); SalesBread publishes a SalesRoads review page. Same template. |  | Not started
A | Comparison | /compare/salesroads-vs-memoryblue | memoryblue vs salesroads; memoryblue alternative | Transactional | Nice-to-have | G2 hosts this comparison. Same template. |  | Not started
A | Comparison | /compare/salesroads-vs-saleshive | saleshive vs salesroads; saleshive alternative | Transactional | Nice-to-have | Same template. |  | Not started
A | Comparison | /compare/salesroads-vs-belkins | belkins vs salesroads; belkins alternative | Transactional | Critical | Semrush #1 organic competitor (27% overlap). Same template. |  | Not started
A | Comparison | /compare/salesroads-vs-callbox | callbox vs salesroads; callbox alternative | Transactional | Important | Same template. |  | Not started
A | Comparison | /compare/salesroads-vs-martal | martal vs salesroads; martal group alternative | Transactional | Nice-to-have | Same template. |  | Not started
B | Pillar rebuild | /appointment-setting-services/ | b2b appointment setting services; outsourced appointment setting; appointment setting company | Commercial | Critical | Merge /outsourcing/outsourced-appointment-setting/ + /outsourcing/everything-to-know-about-b2b-appointment-setting/ (301). Add weeks 1-6 timeline, pricing summary, 3 case-study results, industries grid, FAQs. 2,000+ words unique. |  | Not started
B | Pillar rebuild | /outsourced-sdr-services/ | outsourced sdr services; sdr as a service; sdr outsourcing | Commercial | Critical | Merge /outsourcing/sdr-outsourcing/ + /outsourcing/sales-development-services/. Add in-house vs outsourced SDR cost calculator (data from /outsourcing/in-house-sdr-costs/). |  | Not started
B | Pillar rebuild | /outbound-calling-services/ | b2b cold calling services; cold calling outsourcing | Commercial | Important | One H1; process, call-quality controls, case results, FAQs. |  | Not started
B | Guide | /outsourcing/sales-outsourcing-pricing/ (keep URL) | appointment setting cost; cost per appointment; appointment setting pricing | Commercial / Info | Critical | Existing page has 31 kw (Semrush) – build on it. Merge /outsourcing/appointment-setting-pricing-models/ and /tactics/lead-generation-pricing/ into it. Pay-per-appointment vs retainer vs SDR pod, with SalesRoads' own price. |  | Not started
C | Industry | Existing 8 industry pages | <industry> appointment setting; <industry> lead generation | Commercial | Important | Keyword H1, 2 industry case studies, buyer titles, compliance notes, link to 'Best <industry> appointment setting companies' post. |  | Not started
C | Industry | /it-msp-industry/ | msp lead generation; it services appointment setting | Commercial | Nice-to-have | Built from Crewhu and Pantheon case studies. |  | Not started
C | Industry | /professional-services-industry/ | aec lead generation; professional services appointment setting | Commercial | Nice-to-have | Built from Factor case study. |  | Not started
C | Industry | /hr-tech-staffing-industry/ | hr tech lead generation; staffing appointment setting | Commercial | Nice-to-have | Built from Paylocity and Beneflex case studies. |  | Not started
D | Hub | /case-studies/ | b2b appointment setting case study; outsourced sdr results | Commercial | Important | Filterable by industry/service; expand thin studies (Copperweld, Factor, Agility, Safecor, Shell) with metrics. |  | Not started
D | Hub | /industries/ (from /all-industry-pages/) | industries; b2b appointment setting by industry | Navigational | Important | Real H1 + intro; 301 from old URL. |  | Not started
D | Podcast | /podcast/* (42 episodes) | <guest> podcast; sales leadership podcast | Informational | Nice-to-have | 300-600 word summary, takeaways, transcript, meta description per episode. |  | Not started
Groups: A = brand & comparison, B = service pillars & cost guide, C = industries, D = hubs & podcast.

## Blog Cleanup
URL | Action | Notes | Done?
/outsourcing/lead-generation-services/ | Merge | 301 into /lead-generation-services/ (same slug as the service page) or rename to /outsourcing/outbound-lead-generation-guide/
/outsourcing/outsourced-lead-generation/ | Re-angle | Informational ('guide to outsourcing lead gen'); link to /lead-generation-services/
/outsourcing/outsource-lead-generation/ | Merge | 301 into /outsourcing/outsourced-lead-generation/
/outsourcing/outsourced-appointment-setting/ | Keep + re-angle | Semrush: 2.7% of traffic, 27 kw. Re-angle to informational (what it is, pros/cons) and link to /appointment-setting-services/. Merge only if GSC shows both URLs swapping on the same queries.
/outsourcing/everything-to-know-about-b2b-appointment-setting/ | Merge | 301 into /appointment-setting-services/
/outsourcing/call-center-appointment-setting/ | Re-angle | Keep as call-center angle; link to service page
/outsourcing/sdr-outsourcing/ | Merge | 301 into /outsourced-sdr-services/
/outsourcing/sales-development-services/ | Merge | 301 into /outsourced-sdr-services/
/outsourcing/sales-outsourcing-pricing/ | Keep (survivor) | Semrush: 31 kw. Becomes the cost guide; keep URL
/outsourcing/appointment-setting-pricing-models/ | Merge | 301 into /outsourcing/sales-outsourcing-pricing/
/tactics/lead-generation-pricing/ | Merge | 301 into /outsourcing/sales-outsourcing-pricing/
/outsourcing/how-much-does-salesroads-sales-outsourcing-actually-cost/ | Keep + link | Brand pricing explainer; add meta description; link to /pricing/
/outsourcing/lead-generation-vs-appointment-setting/ | Keep (survivor) | Semrush: only one of the three ranking (11 kw)
/tactics/lead-generation-vs-appointment-setting-whats-the-difference/ | Merge | 301 into /outsourcing/lead-generation-vs-appointment-setting/
/outsourcing/salesroads-program-appointment-setting-or-lead-generation/ | Merge | 301 into the same vs guide (add 'which SalesRoads program' section)
/tactics/ultimate-guide-lead-generation/ | Merge | Pick one lead-gen pillar with /tactics/lead-generation/, /tactics/b2b-lead-generation/, /tactics/b2b-lead-generation-meaning/
/tactics/generating-b2b-leads/ | Keep (survivor) + refresh | Semrush: 2.0% of traffic, 61 kw; drop '(2024 Update)' from title
/tactics/lead-generation-tips/ | Merge | 301 into /tactics/generating-b2b-leads/
/tactics/b2b-lead-generation-tips/ | Merge | 301 into /tactics/generating-b2b-leads/
/tactics/lead-generation-strategies/ | Merge | 301 into /tactics/b2b-lead-generation-strategies/
/tactics/b2b-cold-calling-script/ | Merge | Merge with /tactics/cold-calling-scripts/
/tactics/cold-calling-questions/ | Merge | 301 into /tactics/cold-call-questions/ (the one that ranks)
/tactics/lead-gen-funnel-template/ | Merge | Merge with /tactics/lead-generation-funnel/
/tactics/lead-generation-campaign/ | Merge | 301 into /tactics/building-a-lead-generation-campaign/ (118 kw vs 6)
/leadership/lead-generation-courses/ | Refresh | Title '2024: 9 Best B2B Lead Generation Courses' – update list and year
/tactics/cold-calling-effectiveness/ | Refresh | 'Is Cold Calling Still Effective in 2024?' – update data and year
/leadership/lead-generation-specialist-salary/ | Refresh | 'Updated 2024' – refresh salary data
/leadership/sales-and-business-development-courses/ | Refresh in place | 110 referring domains – update list + year; NEVER change URL; add links to service pages
/leadership/ai-in-sales/ | Keep + link | 146 referring domains – add contextual links to SDR / appointment-setting / cold-calling service pages
/tactics/qualifying-leads-definition/ | Keep + CTA | 6.0% of traffic, #2 'define qualify' – add lead-gen service CTA
/leadership/appointment-setting-job-description/ | Keep + CTA | 1.7% of traffic – add 'Hiring an SDR? Compare costs' box
/leadership/lead-generation-job-description/ | Keep + CTA | 1.2% of traffic – same CTA
/leadership/business-development-and-sales-manager-job-description/ | Keep + CTA | 0.7% of traffic; new #13 'manager in business development' (3.6K/mo)
/leadership/sales-development-career/ | Refresh | '…in 2024' – update
/tactics/lead-generation-examples/ | Refresh | '…in 2024' – update
/leadership/best-sales-podcasts/ | Refresh | '2024' – update; feature own podcast
/tactics/social-selling-strategies/ | Refresh | '…in 2023' – update
/podcast/best-sales-and-leadership-strategies-for-2024/ | Fix | Title says 2025, URL says 2024 – align
/leadership/sdr-resume-guide/ | Keep for recruiting or prune | Job-seeker intent; link to /careers/ if kept
/leadership/sdr-cover-letter-sample/ | Keep for recruiting or prune | Job-seeker intent
/leadership/appointment-setting-jobs/ | Keep for recruiting | Has traffic (11 kw); link to /careers/
/leadership/lead-generation-interview-questions/ | Keep for recruiting | Has traffic (5 kw); link to /careers/
/leadership/appointment-setting-quotes/ | Prune or merge | Low buyer value
/leadership/the-3-ai-lessons-every-sales-leader-needs-to-learn-right-now/ | Publish or remove | Noindex but internally linked
Before merging, check GSC clicks and Ahrefs backlinks for each URL and keep the stronger one; always 301 the merged URL.

## Keyword Clusters
Cluster | Example queries | Intent | Target page | Monthly volume | Keyword difficulty | Current rank
Appointment setting | b2b appointment setting services; outsourced appointment setting; appointment setting company | Commercial | /appointment-setting-services/ |  |  | Not in top 9 (sample)
SDR outsourcing | outsourced sdr services; sdr as a service; top outsourced sdr providers for b2b sales | Commercial | /outsourced-sdr-services/ |  |  | Not in top 9 (sample); 'top outsourced sdr providers' #23 (home) and #61 (service page)
Cold calling | b2b cold calling services; cold calling outsourcing; cold calling company | Commercial | /outbound-calling-services/ |  |  | Not in top 9 (sample)
Lead generation | lead generation services (6,600/mo); lead generation companies (4,400/mo); outsourced lead generation | Commercial | /lead-generation-services/ |  |  | Ranks with SERP feature (Semrush); 21% of traffic
Sales outsourcing | sales outsourcing company; outsourced sales team; b2b telesales companies | Commercial | / |  |  | Page 1 (sample); 'b2b telesales companies' #49
Pricing / cost | appointment setting cost; cost per appointment; sales outsourcing cost; sdr cost | Commercial / Info | /pricing/ + cost guide |  |  | Not in top 9 (sample)
Brand / comparison | salesroads reviews; salesroads alternatives; <competitor> vs salesroads | Transactional | Reviews page + /compare/* |  |  | Third parties own SERP
Industry | saas / healthcare / fintech / manufacturing / government appointment setting | Commercial | Industry pages
Cold calling how-to | cold calling scripts; cold call opening lines; cold calling objections | Informational | /tactics/cold-calling-scripts/ etc.
SDR management | sdr metrics; sdr onboarding; sdr vs bdr; sdr ae (70/mo); sdr salary | Informational | /leadership/* posts |  |  | 'sdr ae' #23
Hiring / job descriptions | appointment setter job description; lead generation job description; manager in business development (3,600/mo) | Info (hiring managers) | /leadership/*-job-description/ |  |  | 'manager in business development' #13; 3 posts = 3.6% of traffic
Definitions | define qualify (2,900/mo); sales executive meaning | Informational | /tactics/qualifying-leads-definition/, /leadership/sales-executive-meaning/ |  |  | 'define qualify' #2
Volumes and difficulty: fill from Semrush / Ahrefs / Google Keyword Planner. 'Current rank' notes come from a single SERP sample on 2026-10-01; replace with tracked positions.

## Semrush Data
Semrush Data – salesroads.com (US, desktop, exports dated 2026-10-01)
Source: client-provided Semrush Domain Overview, Organic Research: Pages and Organic Position Changes exports. Peak traffic is read from the trend chart (approximate).
Metric | Value |  |  |  |  | Note
Organic traffic / month | 3100 |  |  |  |  | +6% MoM; ~40% below 2025 peak (~5.5K)
2025 peak traffic (approx.) | 5500 |  |  |  |  | Read from Semrush trend chart
Ranking keywords | 4083 |  |  |  |  | 72.7% informational, 21.9% commercial, 3.5% transactional
Keywords in positions 1-3 | 85
Keywords in positions 4-10 | 285
Keywords in positions 11-20 | 453 |  |  |  |  | Striking distance – refresh these first
Backlinks | 12000 |  |  |  |  | 60% follow
Referring domains | 2000 |  |  |  |  | Top referrers are directories/list sites
Branded traffic share | 22.9% |  |  |  |  | 45 branded keywords, 718 visits
Paid keywords | 0 |  |  |  |  | No Google Ads
Change from peak | -43.64% |  |  |  |  | Formula: current / peak - 1
Top pages by share of organic traffic
URL | Traffic % | Keywords |  |  |  | Note
/ | 25.57% | 386
/lead-generation-services/ | 21.33% | 165 |  |  |  | Protect – see C-10 redirect chains
https://www.salesroads.com/ | 11.95% | 34 |  |  |  | Separate www homepage – see C-09
/appointment-setting-services/ | 10.01% | 152
/tactics/qualifying-leads-definition/ | 5.99% | 56 |  |  |  | #2 'define qualify' – add service CTA (I-14)
/leadership/sales-executive-meaning/ | 3.6% | 62
/outsourcing/outsourced-appointment-setting/ | 2.67% | 27 |  |  |  | Ranks on its own – re-angle, don't blindly merge
/tactics/generating-b2b-leads/ | 2% | 61 |  |  |  | Survivor of lead-gen tips merge
/outsourced-sdr-services/ | 1.84% | 60
/leadership/appointment-setting-job-description/ | 1.72% | 59 |  |  |  | Hiring-manager traffic – add CTA (I-14)
/careers/ | 1.27% | 7
/tactics/targeted-lead-generation/ | 1.21% | 17
/leadership/lead-generation-job-description/ | 1.21% | 37
/tactics/financial-advisors-appointment-setting-services/ | 1.17% | 13
/leadership/business-development-and-sales-manager-job-description/ | 0.73% | 56
/tactics/value-proposition/ | 0.63% | 6
/tactics/saas-lead-generation-strategies/ | 0.63% | 29
/tactics/sales-competency-development/ | 0.41% | 17
/tactics/account-based-marketing-strategies/ | 0.38% | 102
/leadership/sales-development-representative/ | 0.35% | 25
Top 4 URLs combined | 68.86%
New rankings on 2026-09-30 (Position Changes export)
Keyword | Position | Volume | KD | Intent | Traffic change | URL
manager in business development | 13 | 3600 | 31 | informational | 18 | /leadership/business-development-and-sales-manager-job-description/
leads inbound | 3 | 140 | 9 | informational | 4 | /tactics/types-of-lead-generation/
appointment setting goals | 8 | 170 | 8 | informational | 2 | /tactics/appointment-setting-goals/
b2b lead generation pain points solutions | 3 | 40 | 12 | informational | 2 | /tactics/lead-generation-challenges/
how to follow up on clients | 60 | 40 | 31 | informational | 0 | /tactics/sales-follow-ups/
strategies to close more leads for business | 67 | 40 | 12 | informational | 0 | /tactics/sales-closing-techniques/
customizable phone script | 55 | 110 | 4 | informational | 0 | /tactics/cold-calling-scripts/
sdr trade | 63 | 40 | 24 | informational | 0 | /tactics/sdr-meaning-in-sales/
sdr ae | 23 | 70 | 19 | informational | 0 | /leadership/sdr-vs-ae/
cost to outsource it | 33 | 70 | 26 | informational | 0 | /outsourcing/sales-outsourcing-pricing/
how to become a sales development representative | 48 | 50 | 28 | informational | 0 | /leadership/sdr-training/
top outsourced sdr providers for b2b sales | 23 | 40 | 24 | commercial | 0 | /
top outsourced sdr providers for b2b sales | 61 | 40 | 24 | commercial | 0 | /outsourced-sdr-services/
icp meaning finance | 74 | 40 | 23 | informational | 0 | /tactics/icp-sales/
what is the impact of personalized outreach on lead conversion | 17 | 40 | 18 | informational | 0 | /tactics/personalized-sales-outreach/
social selling meaning | 41 | 50 | 37 | informational | 0 | /tactics/social-selling-vs-traditional-selling/
how to make cold calls | 21 | 170 | 36 | informational | 0 | /tactics/b2b-cold-calling/
appointment setting solutions | 36 | 70 | 20 | informational | 0 | /tactics/appointment-setting-funnel/
tech companies channel sales strategy challenges | 61 | 50 | 12 | informational | 0 | /tactics/channel-sales-development/
lead generation job profile | 77 | 90 | 14 | commercial | 0 | /leadership/lead-generation-specialist-salary/
b2b telesales companies | 49 | 110 | 19 | commercial, informational | 0 | /
Top organic competitors (keyword overlap)
Competitor | Competition level | Common keywords | SE keywords |  |  | Use
belkins.io | 27% | 301 | 6000 |  |  | Comparison page candidate (Content Plan)
superhumanprospecting.com | 20% | 172 | 2600 |  |  | Comparison page candidate (Content Plan)
salesfocusinc.com | 19% | 188 | 4900 |  |  | Comparison page candidate (Content Plan)
callboxinc.com | 18% | 318 | 8900 |  |  | Comparison page candidate (Content Plan)
salesbread.com | 15% | 200 | 5200 |  |  | Comparison page candidate (Content Plan)

## External Checks
Check | Why not verified | Tool | Result / Notes
Core Web Vitals (LCP, INP, CLS) field data | Needs CrUX / real-user data | PageSpeed Insights; GSC > Core Web Vitals
Index coverage; excluded URLs | Needs Search Console access | GSC > Pages
Cannibalization by query | Needs Search Console access | GSC > Performance > filter query > Pages tab
Exact rankings and search volume | SERP checks were a point-in-time sample | Semrush / Ahrefs position tracking
Backlinks per merge candidate | Semrush export covers top 5 pages only | Semrush Backlinks > Indexed Pages / Ahrefs / GSC > Links
www > apex redirect (HIGH – Semrush shows www ranking, C-09) | Audit proxy blocked www.salesroads.com | curl -sI https://www.salesroads.com/; GSC URL Inspection
What consortiumventure24.com/js/812387.js is | Audit proxy blocked the domain | Google Tag Assistant; ask marketing ops
Rendered DOM / JS-dependent content | Raw-HTML crawl only | Screaming Frog (JS rendering); GSC URL Inspection

## Sources
Source | URL
SalesRoads homepage | https://salesroads.com/
robots.txt | https://salesroads.com/robots.txt
Sitemap index | https://salesroads.com/sitemap_index.xml
Pricing | https://salesroads.com/pricing/
Reviews | https://salesroads.com/reviews/
Appointment setting services | https://salesroads.com/appointment-setting-services/
VSA landing page | https://salesroads.com/vsa/
WP users endpoint | https://salesroads.com/wp-json/wp/v2/users
G2 – SalesRoads alternatives | https://www.g2.com/products/salesroads/competitors/alternatives
G2 – SalesRoads vs memoryBlue | https://www.g2.com/compare/salesroads-vs-memoryblue
Cleverly – SalesRoads review | https://www.cleverly.co/blog/salesroads-reviews
SalesBread – SalesRoads review | https://salesbread.com/salesroads/
Salesforge – SalesRoads review | https://www.salesforge.ai/blog/salesroads-review
OutboundSalesPro – SalesRoads review | https://outboundsalespro.com/salesroads-review/
Alleyoop – SalesRoads alternative | https://alleyoop.io/salesroads-alternative/
RemoteAides – SalesRoads alternatives | https://www.remoteaides.com/salesroads-reviews-and-best-cold-calling-agency-alternatives/
Sales Focus – appointment setting | https://www.salesfocusinc.com/sales-outsourcing/appointment-setting/
UnboundB2B – best appointment setting companies | https://www.unboundb2b.com/blog/best-b2b-appointment-setting-companies-in-the-usa/
Callbox – outsourced SDR | https://www.callboxinc.com/outsourced-sdr-services/
memoryBlue – SDR services | https://memoryblue.com/sdr-services/
Belkins – appointment setting cost | https://belkins.io/blog/appointment-setting-costs-pricing-models
Leadium – appointment setting pricing | https://www.leadium.com/blog/appointment-setting-services
Clutch – sales outsourcing rankings | https://clutch.co/us/call-centers/sales-outsourcing
Shodan – consortiumventure24.com host | https://www.shodan.io/host/51.11.20.152
Semrush exports (client-provided, 2026-10-01): Domain Overview, Organic Pages, Position Changes | https://www.semrush.com/