## Summary
SEO Audit: crewhu.com
Audit date | 2026-10-01
Site | https://www.crewhu.com/
Overall health | Needs Work
Method | Based on search-engine index data, competitor SERPs and third-party listings. Direct access to crewhu.com was blocked, so HTML-level items are marked 'verify' (see External Checks).
Findings by priority
Priority | Total | Done | Open | % Done
Critical
Important
Nice-to-have
Total
Top critical issues
C-01 | Duplicate free-trial / demo landing pages indexed
C-02 | Generic one-word titles on core commercial pages
C-03 | Competitors own 'Crewhu alternative' and comparison SERPs
C-04 | No ranking page for '<PSA> CSAT survey' queries
C-05 | Integration docs live on get-help-tnt.crewhu.com subdomain
What's working
Homepage title is strong: brand + both categories + audience.
/blog/how-to-get-more-google-reviews ranks #1 for 'how to get more Google reviews for MSP'.
/blog/employee-recognition-software ranks for 'employee recognition software for MSPs'.
Strong proof points: GO2 Tech (600% more Google reviews), Kraft (45% YoY growth), ACE IT (99% CSAT), 4.7★ on G2 (94 reviews).
Tabs
Action Tracker | All findings with priority, recommendation, owner and status
Quick Wins | Top 5 actions to do first
Title & Meta Rewrites | Copy-paste titles/metas with length checks
Content Plan | New pages to build, with target queries and briefs
Blog Cleanup | Merge / refresh / prune decisions for existing posts
Keyword Clusters | Target clusters; fill in volumes from your SEO tool
External Checks | Items to verify with GSC, Screaming Frog, PSI, Ahrefs
Sources | Evidence URLs

## Action Tracker
Crewhu.com SEO Audit – Action Tracker
Yellow columns (Owner, Due Date, Status, Notes) are for your team to fill in. Status options: Not started / In progress / Done / Won't fix.
ID | Category | Priority | Finding | Affected URLs / Evidence | Why it matters | Recommendation | Effort | Impact | Owner | Due Date | Status | Notes
C-01 | Technical | Critical | Duplicate free-trial / demo landing pages indexed | /start-free-trial, /free-trial-3, /free-trial-g2, /book-a-crewhu-demo-today | Pages compete for the same intent, split link equity, and send organic visitors to G2/paid campaign pages. | Pick one canonical /free-trial and /demo URL. Add noindex,follow (or rel=canonical) to all campaign variants; remove them from the XML sitemap; audit GSC for other -2/-4 variants. | Low | High | SEO lead |  | Not started | Example row - replace with your owner
C-02 | On-Page | Critical | Generic one-word titles on core commercial pages | /products, /integrations, /about-us, /collect-customer-feedback, /gamify-your-metrics | Highest-intent pages give Google almost no keyword signal and earn low CTR. | Apply the rewrites in the 'Title & Meta Rewrites' tab. | Low | High |  |  | Not started
C-03 | Content | Critical | Competitors own 'Crewhu alternative' and comparison SERPs | simplesat.io/alternatives/crewhu-alternative; G2/Capterra/GetApp | Bottom-of-funnel buyers see competitor framing (and outdated pricing) instead of Crewhu's. | Build /compare/crewhu-vs-simplesat, -vs-smileback, -vs-bonusly, -vs-nicereply plus competitor-alternatives pages (see Content Plan). | Medium | High |  |  | Not started
C-04 | Content | Critical | No ranking page for '<PSA> CSAT survey' queries | Search: 'ConnectWise CSAT survey integration' | Simplesat, SmileBack and BizRatings rank; Crewhu is absent. Integration info only exists in help docs. | Create /integrations/<psa> landing pages (ConnectWise, Autotask, HaloPSA, Kaseya BMS, Syncro, Zendesk, etc.). | Medium | High |  |  | Not started
C-05 | Technical | Critical | Integration docs live on get-help-tnt.crewhu.com subdomain | get-help-tnt.crewhu.com/hc/en-us/... | Subdomain authority largely doesn't benefit www; 'tnt' looks like a test environment. | Short term: link each help article to its marketing integration page. Medium term: move to help.crewhu.com or /help with 301s. | Medium | Medium |  |  | Not started
I-01 | On-Page | Important | Non-descriptive URL slugs | /book-a-crewhu-demo-today, /free-trial-3, /gamify-your-metrics, /collect-customer-feedback | Slugs carry little keyword value. | Consider /demo, /free-trial, /gamification, /csat-surveys - only with 301 redirects and only for top pages. | Medium | Low |  |  | Not started
I-02 | On-Page | Important | 'Ask Ashley' posts have vague titles | /ask-ashley/ask-ashley-take-one | Titles don't match any search query. | Retitle each post after the question it answers; keep 'Ask Ashley' as an in-body series label. | Low | Medium |  |  | Not started
I-03 | Technical | Important | Structured data not confirmed (verify) | Homepage, /pricing, blog | Missing schema forfeits rich results and entity clarity. | Add SoftwareApplication (offers $119/$239/$399, aggregateRating if reviews shown on page), Organization with sameAs, Article/BlogPosting with author, BreadcrumbList, FAQ content. | Low | Medium |  |  | Not started
I-04 | Technical | Important | Blog dates inconsistent / stale posts mixed with 2026 content | /blog/* | Mismatched datePublished/dateModified confuses freshness signals. | Align schema dates with visible dates; refresh or merge old posts. | Low | Low |  |  | Not started
I-05 | Content | Important | Off-topic / drifting blog posts | /blog/games-for-employee-training, /blog/smart-goal-examples-for-employees, /blog/ebitda-for-msps, /blog/the-daily-huddle-... | Dilutes MSP topical authority. | Refresh with MSP angle if they get traffic; prune or noindex thin pre-2023 posts with no traffic or links. | Medium | Medium |  |  | Not started
I-06 | Content | Important | Two overlapping 'employee recognition platforms' guides | /blog/a-guide-to-employee-recognition-platforms-..., /blog/employee-recognition-software | Keyword cannibalization. | 301 the older guide into /blog/employee-recognition-software. | Low | Medium |  |  | Not started
I-07 | Content | Important | Only one case study indexed | /case-study/go2-tech | Kraft (45% YoY growth) and ACE IT (99% CSAT) proof isn't searchable. | Build /customers hub; publish each story as its own page with metric-led titles. | Medium | Medium |  |  | Not started
I-08 | Content | Important | Weak internal linking from blog to commercial pages | /blog/* | Ranking blog posts don't pass authority or visitors to product pages. | Every post links to ≥1 product/integration/comparison page with descriptive anchor text. | Low | Medium |  |  | Not started
I-09 | Off-Site | Important | Outdated pricing on review sites | Capterra, GetApp, SourceForge, Software Advice | '$99/user/month' conflicts with $119/$239/$399 plans. | Claim profiles and update pricing; drive fresh G2/Capterra reviews. | Low | Medium |  |  | Not started
N-01 | Technical | Nice-to-have | Core Web Vitals not measured (verify) | Sitewide | Chat widgets, video and trackers often hurt LCP/INP. | Defer chat/analytics, use WebP/AVIF with explicit dimensions; check PageSpeed Insights. | Medium | Low |  |  | Not started
N-02 | Off-Site | Nice-to-have | Partner/marketplace backlinks underused | Pax8, ConnectWise Marketplace, HaloPSA, Kaseya | Relevant, authoritative links available. | Request integration listings linking to /integrations/<psa> pages; pitch benchmark report to ChannelPro, SmarterMSP, MSP Insights. | Medium | Medium |  |  | Not started
N-03 | On-Page | Nice-to-have | Homepage title could lead with CSAT | / | CSAT/NPS queries carry stronger buying intent. | Optional test: 'Crewhu: CSAT & Employee Recognition Software for MSPs'. | Low | Low |  |  | Not started

## Quick Wins
Quick Wins – do these first
# | Action | Tracker ID | Est. effort | Status (from tracker)
1 | Noindex/canonicalize duplicate trial & demo pages; remove from sitemap | C-01 | ~30 min
2 | Rewrite generic titles & meta descriptions (see 'Title & Meta Rewrites') | C-02 | ~1-2 hrs
3 | Add SoftwareApplication + Organization schema to homepage and /pricing | I-03 | ~1 hr
4 | Publish first comparison page: /compare/crewhu-vs-simplesat | C-03 | ~1-2 days
5 | Link help-center integration articles to marketing pages; link Google-reviews blog post to GO2 Tech case study + trial | C-05 / I-08 | ~2 hrs

## Title & Meta Rewrites
URL | Current title (as indexed) | Proposed title | Proposed meta description | Title length | Meta length
/products | Products | Crewhu Products: CSAT, Recognition & Gamification for MSPs | One platform for MSP client feedback and team engagement: one-click CSAT and NPS surveys, peer recognition, badges, rewards and PSA-powered contests.
/integrations | Integrations | Crewhu Integrations: ConnectWise, Autotask, HaloPSA & More | Connect Crewhu to ConnectWise, Autotask, HaloPSA, Syncro, Zendesk, Teams, Slack and BrightGauge. Surveys sync to tickets; wins reach your team.
/collect-customer-feedback | Collect Customer Feedback | CSAT & NPS Survey Software for MSPs ¦ Crewhu | Send one-click CSAT surveys on every closed ticket and automated NPS surveys, then turn happy clients into Google reviews. Built for MSPs.
/gamify-your-metrics | Gamify Your Metrics | Help Desk Gamification & Technician Leaderboards ¦ Crewhu | Run contests and leaderboards on real PSA KPIs (CSAT, closed tickets, time entries) to motivate MSP technicians.
/about-us | About Us | About Crewhu: Built by an MSP Veteran for MSPs | Founded in 2013 by Stephen Spiegel, Crewhu helps MSPs delight clients and engage their teams with CSAT, recognition and gamification.
/pricing | Pricing & Plans: Employee Recognition Software | Crewhu Pricing & Plans: CSAT + Recognition for MSPs | Compare Crewhu plans: Listen ($119/mo), Recognize ($239/mo) and Grow ($399/mo). Start a free 14-day trial, no credit card required.
/ask-ashley/ask-ashley-take-one | Ask Ashley, Take One | (Retitle after the question the post answers) | (Write after retitling)
Lengths highlighted yellow exceed ~60 chars (title) / ~160 chars (meta) and may be truncated in search results. Current titles are as indexed by search engines and should be confirmed against page source.

## Content Plan
Group | Type | Proposed URL | Target queries | Intent | Priority | Brief / key elements | Owner | Status
A | Comparison | /compare/crewhu-vs-simplesat | crewhu vs simplesat, simplesat alternative | Transactional | Critical | Positioning (feedback-only vs feedback + recognition + gamification), feature table, pricing, best-fit, quotes, FAQ |  | Not started
A | Comparison | /compare/crewhu-vs-smileback | crewhu vs smileback, smileback alternative | Transactional | Critical | Same template |  | Not started
A | Comparison | /compare/crewhu-vs-bonusly | bonusly vs crewhu | Transactional | Important | Same template; recognition angle |  | Not started
A | Comparison | /compare/crewhu-vs-nicereply | nicereply alternative msp | Transactional | Important | Same template |  | Not started
A | Alternatives | /smileback-alternatives, /simplesat-alternatives | smileback alternatives, simplesat alternatives | Commercial | Important | Fair roundup listing Crewhu first with clear best-fit guidance |  | Not started
B | Integration | /integrations/connectwise | connectwise csat survey, connectwise nps | Commercial | Critical | What syncs, write-back to notes/custom fields, setup time, screenshot, quote, help-doc link |  | Not started
B | Integration | /integrations/autotask | autotask csat survey | Commercial | Critical | Same template |  | Not started
B | Integration | /integrations/halopsa | halopsa csat survey | Commercial | Important | Same template; reference new custom-field write-back |  | Not started
B | Integration | /integrations/kaseya-bms, /syncro, /zendesk, /freshdesk, /cloudradial | <psa> csat survey | Commercial | Important | Same template |  | Not started
B | Integration | /integrations/teams, /slack, /brightgauge, /it-glue, /power-bi | <tool> recognition / csat dashboard | Commercial | Nice-to-have | Same template |  | Not started
C | Solution | /solutions/google-review-generation-for-msps | msp review software, get google reviews msp | Commercial | Important | GO2 Tech 600% proof; compliant (no review gating) positioning |  | Not started
C | Solution | /solutions/technician-retention | msp technician retention, help desk burnout | Informational | Important | Cite Auvik (60% burned out), Gallup (2.6x job seeking) |  | Not started
C | Solution | /solutions/nps-for-msps | nps for msps, relational nps survey | Commercial | Important | Link NPS benchmarks blog post |  | Not started
C | Solution | /gamification | help desk gamification, technician leaderboard | Commercial | Important | Expand current /gamify-your-metrics page |  | Not started
D | Proof | /customers (hub) + Kraft + ACE IT pages | crewhu case study, msp csat case study | Commercial | Important | Metric-led titles, e.g. 'How ACE IT Hit 99% CSAT and Cut Stale Tickets 50%' |  | Not started
E | Linkable asset | /msp-csat-nps-benchmark-report | msp csat benchmark, it services nps benchmark | Informational | Important | Anonymized platform data; annual; pitch to MSP media |  | Not started
E | Tool | /tools/nps-calculator | nps calculator | Informational | Nice-to-have | Simple calculator + CTA |  | Not started
E | Tool | /tools/google-review-link-generator | google review link generator | Informational | Nice-to-have | Link + QR generator for MSPs |  | Not started
E | Template | /resources/msp-csat-survey-templates | csat survey template msp | Informational | Nice-to-have | Downloadable/copyable templates |  | Not started

## Blog Cleanup
URL | Action | Notes | Done?
/blog/a-guide-to-employee-recognition-platforms-and-improving-your-bottom-line | Merge | 301 into /blog/employee-recognition-software (cannibalization)
/blog/games-for-employee-training | Refresh or prune | 2023, off-topic; reframe for MSP technician training or noindex if no traffic
/blog/smart-goal-examples-for-employees | Refresh | Reframe: 'SMART Goal Examples for MSP Technicians'; link to /gamification
/blog/ebitda-for-msps | Keep + link | Relevant to MSP owners; fix date inconsistency; link to retention/CSAT pages
/blog/the-daily-huddle-a-game-changer-for-company-culture | Refresh | Add MSP service-desk angle; link to recognition product
/blog/how-testimonials-reviews-help-sales-marketing | Refresh + link | 2022; link to Google-reviews solution page and GO2 Tech
/blog/how-to-get-more-google-reviews | Protect + link | Ranks #1; add links to GO2 Tech case study and trial
/blog/employee-recognition-software | Protect + link | Ranks for 'employee recognition software for MSPs'; keep updated yearly

## Keyword Clusters
Cluster | Example queries | Intent | Target page | Monthly volume | Keyword difficulty | Current rank
CSAT for MSPs | csat software for msps; msp customer satisfaction survey; csat survey tool connectwise | Commercial | /csat-surveys + /integrations/*
NPS | nps for msps; relational nps survey; good nps score it services | Commercial / Info | /solutions/nps-for-msps; NPS benchmarks post
Recognition | employee recognition software for msps; technician recognition program | Commercial | /employee-recognition + comparison blog post
Gamification | gamification for help desk; technician leaderboard; service desk gamification | Commercial | /gamification
Reviews | how to get google reviews msp; msp review software | Info / Commercial | Reviews blog post + review-generation solution page
Comparisons | crewhu vs smileback; simplesat alternative; smileback alternatives | Transactional | /compare/*
Retention | msp technician retention; help desk burnout | Informational | Retention solution page + blog
Volume, difficulty and rank were not available in this audit – fill from Ahrefs, Semrush or Google Keyword Planner.

## External Checks
Check | Why not verified | Tool | Result / Notes
Raw HTML: meta descriptions, H1s, canonicals, alt text, schema | crewhu.com blocked by audit network policy | Screaming Frog; Google Rich Results Test
robots.txt / XML sitemap contents | Same | Open /robots.txt and /sitemap.xml; GSC > Sitemaps
Index coverage, duplicates, queries | Requires owner access | Google Search Console > Pages, Performance
Core Web Vitals | Requires live render | PageSpeed Insights; CrUX in GSC
Backlink profile & link gap vs simplesat.io / smileback.com | Requires link index | Ahrefs; Semrush
Keyword volumes | Not available | Ahrefs; Semrush; Google Keyword Planner

## Sources
Source | URL
Crewhu homepage | https://www.crewhu.com/
Products | https://www.crewhu.com/products
Integrations | https://www.crewhu.com/integrations
Pricing | https://www.crewhu.com/pricing
Start free trial | https://www.crewhu.com/start-free-trial
Free trial 3 | https://www.crewhu.com/free-trial-3
Free trial G2 | https://www.crewhu.com/free-trial-g2
Book a demo | https://www.crewhu.com/book-a-crewhu-demo-today
GO2 Tech case study | https://www.crewhu.com/case-study/go2-tech
Employee recognition software post | https://www.crewhu.com/blog/employee-recognition-software
Google reviews post | https://www.crewhu.com/blog/how-to-get-more-google-reviews
Ask Ashley | https://www.crewhu.com/ask-ashley/ask-ashley-take-one
Help center integrations | https://get-help-tnt.crewhu.com/hc/en-us/sections/360000298233-Integrations
Simplesat Crewhu alternative | https://www.simplesat.io/alternatives/crewhu-alternative
Simplesat ConnectWise | https://www.simplesat.io/integrations/connectwise
ConnectWise Customer Feedback (SmileBack) | https://www.connectwise.com/platform/business-management/smileback
Capterra | https://www.capterra.com/p/140426/CrewHu/
GetApp | https://www.getapp.com/hr-employee-management-software/a/crewhu/
G2 alternatives | https://www.g2.com/products/crewhu/competitors/alternatives
NetSuite MSP challenges 2026 | https://www.netsuite.com/portal/resource/articles/business-strategy/msp-challenges.shtml
LTVplus technician burnout | https://www.ltvplus.com/msp/msp-technician-burnout/